SOP TEMPLATE

# Change request procedure

| SOP no. |  | Version |  | Effective date |  |
| --- | --- | --- | --- | --- | --- |
| Owner |  | Approver |  | Review date |  |

# Purpose

To make sure work outside the agreed scope is quoted and approved before it starts, so budgets and deadlines stay realistic.

# Scope

Every request for new or changed work on a fixed-scope project.

# Responsibilities

| Role | Responsibility |
| --- | --- |
| Project manager | Logs the request, checks it against scope, gets the estimate and the approval. |
| Team lead | Estimates the work and its effect on the timeline. |
| Client | Approves or declines the change in writing. |

# Procedure

- Log the request

Record what the client asked for, who asked, and when.

- Check it against the scope

Decide whether it is in scope, a fix, or new work.

- Estimate it

Estimate the hours, the cost and the effect on the deadline.

- Send the change request

Send the client a short change request with the work, cost and new dates.

Caution: Don’t start the work until the client approves it in writing.

- Update the plan

Once approved, update the timeline, budget and tasks, and tell the team.

# Records

- The change log for each project.

- Each approved or declined change request.

# Related documents

- Project kickoff checklist

# Revision history

| Version | Date | What changed | Approved by |
| --- | --- | --- | --- |